## Registration
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_REG_01 | "text_success" message appears after clicking on Forgot Password with a valid email | New | Developer | Ghada Amr | Chrome v141 | FP_03 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on "Login" 4- Click on "Forgot Password" 5- Input the email in the Email field (testerfortesting@grr.la) 6- Click on "Continue" button | "Reset link was sent successfully" confirmation message should appear | "text_success" message appears which is not context appropriate | Low | Low
BUG_REG_02 | No email with a password reset link was received in the email inbox after clicking on Forgot Password | New | Developer | Ghada Amr | Chrome v141 | FP_06 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on "Login" 4- Click on "Forgot Password" 5- Input the email in the Email field (testerfortesting@grr.la) 6- Click on "Continue" button 7- Check email inbox at the link: https://www.guerrillamail.com/inbox | Clicking on the "Continue" button after entering a valid email send an email to the user's email inbox with a password reset link | No email with a password reset link was found in the inbox | High | Critical

## Account
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_ACC_01 | Clicking on the "Continue" button on the "Edit Address" page after adding valid address information fails to navigate to the Address Book page | New | Developer | Ghada Amr | Chrome v141 | AB_21 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on "Address Book" in the Account Sidebar Menu 5- Click on "Add Address" 6- Add valid information (First Name: tester / Last Name: tester / address 1: Tester street / City: Tester city / Post Code: 12345 / Country: United Kingdom / City: Durham) 7- Click on "Continue" button 8- Click on the "Edit" button next to the address 9- Click on the "Continue" button | Clicking on the "Continue" button navigates the user back to the Address Book page | Clicking on the Continue does not navigate the user to the Address Book page | High | Major
BUG_ACC_02 | Adding an address without choosing a country or a region/state leads to a blank box displayed in the list of addresses in the "Address Book" page | New | Developer | Ghada Amr | Chrome v142 | AB_22 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" 4- Click on "Address Book" in the Account Sidebar Menu 5- Click on "Add Address" 6- Add valid information (First Name: tester / Last Name: tester / address 1: Tester street / City: Tester city / Post Code: 12345 / Country: United Kingdom / City: Durham) 7- Click the "Continue" button 7- Click on the "Edit" button next to the address 8- Change the Country to " --- Please Select --- " 9- Change the Region / State to " --- None --- " 10- Click on the "Continue" button | Address information displayed in the "Address Book" page should reflect the edits made | When removing the Country selection and the Region/State selection and changing them to "---Please Select---", the address displayed in the "Address Book" page is blank and does not show any of the information saved | High | Major
BUG_ACC_03 | Clicking on the remove button next to a product in the wishlist logs the user out of their account | New | Developer | Ghada Amr | Chrome v141 | WL_08 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on the "opencart" logo to go to the homepage 5- Add "MacBook" to the wishlist 6- Click on "Wish List" in the header | Clicking on the "remove" button removes the product from the "Wishlist" page | Clicking on the remove button next to a product in the wishlist logs the user out of their account | Highest | Critical
BUG_ACC_04 | Subscribing to the newsletter does not send a confiramtion email to the user inbox | New | Developer | Ghada Amr | Chrome v142 | NL_07 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on "Newsletter" in the Account Sidebar Menu 5- Click on the button next to the"Subscribe" 6- Check email inbox for confirmation email | A confirmation email should be received in the user email inbox | No mails were received to the inbox upon subscription to the newsletter | Medium | Moderate
BUG_ACC_05 | No transactions could be made due to admin error | New | Developer | Ghada Amr | Chrome v143 | TS_03 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on "Transactions" in the Account Sidebar Menu | Transactions details should be displayed | New transactions could not be made to test the displayed details | High | Major
BUG_ACC_06 | No ongoing subscriptions could be made due to admin error | New | Developer | Ghada Amr | Chrome v144 | SBS_03 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on "My Account" in the header then click on "My Account" in the dropdown menu 5- Click on "Subscriptions" in the Account Sidebar Menu | Active subscription details (Product Name, Status, Next Payment Date, and Amount) are displayed. | New ongoing subscriptions could not be made to test the displayed details | Highest | Major
BUG_ACC_07 | No downloads could be made due to admin error | New | Developer | Ghada Amr | Chrome v145 | DL_03 | 1- Go to the website: https://demo.opencart.com/en-gb?route=common/home 2- Click on "Account" in the header at the top of the page 3- Click on Login and enter valid credentials then click on "login" (email: testerfortesting@grr.la / password: testing) 4- Click on the "opencart" logo to go to the homepage 5- Click on "Software" in the navigation panel 6- Add any downloadable software to cart 7- Click on "Shopping Cart" in the header 8- Complete Checkout 9- Click on "My Account" in the header then click on "My Account" in the dropdown menu 10- Click on "Downloads" in the Account Sidebar Menu | Previous downloadable order details are displayed in the "'Downloads" page | New downloads could not be made to test the displayed details | Highest | Major

## Product Browsing
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_PP_01 | Incorrect product images displayed when clicking alternate thumbnails | open | Developer | Mohamed | win 11 pro - chrome | PP_02 | 1. Go to the website: https://demo.opencart.com/ 2. Open the product page for a product with multiple images 3. Look for thumbnail/alternate view images below/near the main image 4. Click each thumbnail to change the main image | Alternate thumbnails are displayed and clicking them updates the main image | Other product Images shown | High | Major
BUG_PP_02 | Discounted price not clearly visible or formatted | open | Developer | Mohamed | win 11 pro - chrome | PP_12 | 1. Go to the website: https://demo.opencart.com/ 2. Open product page for discounted product 3. Observe original price and discounted price presentation | Discounted price is displayed and original price is struck-through or shown appropriately | Discounted price is not displayed clearly | Medium | Moderate
BUG_PP_03 | Quantity field allows invalid input without showing validation | open | Developer | Mohamed | win 11 pro - chrome | PP_15 | 1. Go to the website: https://demo.opencart.com/ 2. Open product page 3. Enter a numeric value in quantity field and try to add to cart 4. Enter invalid input ("test") and verify validation | Quantity accepts numbers; invalid input prevented or corrected with validation message | No error massage | High | Major
BUG_PP_04 | Invalid quantity can be added to cart without validation | open | Developer | Mohamed | win 11 pro - chrome | PP_16 | 1. Go to the website: https://demo.opencart.com/ 2. Open product page 3. Enter (1) quantity and click Add to Cart 4. Observe validation/error messages | System shows appropriate validation messages and prevents invalid quantity | added to cart withour error massage | High | Critical
BUG_PP_05 | “Write Review” link is unresponsive | open | Developer | Mohamed | win 11 pro - chrome | PP_23 | 1. Go to the website: https://demo.opencart.com/ 2. Open product page 3. Click on 'Write a review' link 4. Observe redirect to review tab or form | Write review link opens the review form/tab | not clickabe | Medium | Major
BUG_CMP_01 | Alternate images not updating on compare page | open | Developer | Mohamed | win 11 pro - chrome | CMP_07 | 1. Go to the website: https://demo.opencart.com/ 2. On Compare page,change product images 3. Observe displayed image changes accordingly | Alternate images update correctly on compare page | Just orginal image | Medium | Major
BUG_CP_01 | Incorrect category products shown on Desktops page | open | Developer | Mohamed | win 11 pro - chrome | CP_25 | 1. Go to the website: https://demo.opencart.com/ 2. Click 'Desktops' link in side menu or top menu 3. Observe navigation to Desktops category page | User is redirected to Desktops page | Products are not related to desktops category | Medium | Major
BUG_CP_02 | Category filter not returning products | open | Developer | Mohamed | win 11 pro - chrome | CP_29 | 1. Go to the website: https://demo.opencart.com/ 2 .In the search bar (top right), enter the keyword “Monitors” and press Enter. 3.Observe the search results page displaying | The page should display only the products belonging to the selected category | No results shown | High | Critical

## Cart Management
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_CART_01 | When clicking the “Add to Cart” icon on some featured products, the user is redirected to the product details page instead of adding the item directly to the cart. | New | Developer | Menna | OpenCart Local v.3.x | CART_02 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). | The product should be added to the cart directly without leaving the page. | Clicking the “Add to Cart” icon redirects to the product page instead of adding the item to the cart. | High | Major
BUG_CART_02 | Entering a negative quantity (e.g., “-1”) in the Shopping Cart automatically removes the product instead of showing an error or validation message. | New | Developer | Menna | OpenCart Local v.3.x | CART_11 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. In the “Quantity” field, enter “-1” for any product. 6. Press the update (🔄) button. | The system should display a validation error message indicating that the quantity cannot be less than 1. | The product is removed from the cart without any error message. | Medium | Major
BUG_CART_03 | When entering an excessively large quantity (e.g., a number with many digits) in the Shopping Cart, the product is automatically removed instead of showing an error or validation message. | New | Developer | Menna | OpenCart Local v.3.x | CART_11 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. In the “Quantity” field, enter “9999999999999999..” for any product. 6. Press the update (🔄) button. | The system should validate the input and show an error message like “Invalid quantity” or set a maximum allowed limit. | The item is removed from the cart automatically without any warning or error message. | Medium | Major
BUG_CART_04 | Incorrect total price calculation for individual products in the Shopping Cart. The total for each product does not match the unit price multiplied by the quantity. | New | Developer | Menna | OpenCart Local v.3.x | CART_25, CART_27 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5-. Add multiple quantities of the same product (e.g., 3 × iPhone @ $123.20 each). 6. Observe the “Total” column for that product. | The total price should be correctly calculated as Unit Price × Quantity (e.g., 3 × 123.20 = 369.60). | The total is incorrectly calculated as $365.60 instead of $369.60. | High | Critical
BUG_CART_05 | Sub-Total is calculated incorrectly on the Shopping Cart page. | New | Developer | Menna | OpenCart Local v.3.x | CART_12 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5-. Check Sub-Total under the cart summary. | Sub-Total should equal the sum of product totals: (3 × 123.20) + (4 × 602.00) = $2,777.60. | Sub-Total displays $2,303.00. | High | Critical
BUG_CART_06 | “Post Code” field in the “Estimate Shipping & Taxes” form accepts alphabetic characters instead of validating numeric input. | New | Developer | Menna | OpenCart Local v.3.x | CART_37 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. Scroll to “Estimate Shipping & Taxes.” 6. Select any country and region. 7. Enter alphabetic characters (e.g., “JKGFGF”) in the “Post Code” field. 8. Click “Get Quotes.” | The system should validate input and display an error like “Please enter a valid postal code (numbers only).” | The system accepts alphabetic input and applies the shipping estimate successfully. | Medium | Major
BUG_CART_07 | Validation message appears for the wrong field when “Region / State” is not selected in the “Estimate Shipping & Taxes” form. | New | Developer | Menna | OpenCart Local v.3.x | CART_33 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. Scroll to “Estimate Shipping & Taxes.” 6. Select a country (e.g., Afghanistan). 7. Leave the “Region / State” field unselected. 8. Click “Get Quotes.” | The system should display an error message under “Region / State” indicating it is required. | The error message appears under the “Country” field instead, even though the country was already selected. | Medium | Minor
BUG_CART_08 | “Region / State” field displays unnecessary “None” option for countries that do not have administrative regions (e.g., Åland Islands). | New | Developer | Menna | OpenCart Local v.3.x | CART_34 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. Scroll to “Estimate Shipping & Taxes.” 6. Select a country that has no regions (e.g., Åland Islands). | The “Region / State” field should be hidden or disabled for countries without regions. | The dropdown shows “--- None ---” and “--- Please Select ---”, which may confuse users. | Low | Minor
BUG_CART_09 | Shipping rate and method remain constant for all countries and regions in the “Estimate Shipping & Taxes” section. | New | Developer | Menna | OpenCart Local v.3.x | CART_36 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. Scroll to “Estimate Shipping & Taxes.” Select different countries (e.g., Yemen, Germany, USA) and regions. 6. Click “Get Quotes.” | Shipping rate and available shipping methods should vary according to the selected country and region. | The same method (“Flat Shipping Rate - $5.00”) is displayed for all locations. | High | Major
BUG_CART_10 | “Remove” button in the “Use Coupon Code” section does not perform any action. | New | Developer | Menna | OpenCart Local v.3.x | CART_43 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5. Scroll to “Use Coupon Code.” 6. Enter any text in the coupon field. 7. Click “Apply Coupon,” then click “Remove.” | The system should remove the applied coupon or display a message confirming that no coupon was found. | Clicking the “Remove” button has no visible action, message, or change in cart state. | Medium | Major
BUG_CART_11 | Entering alphabetic characters in the “Quantity” field removes the product instead of showing an input validation error. | New | Developer | Menna | OpenCart Local v.3.x | CART_11 | 1. Open the homepage. 2. Go to the “Featured” products section. 3. Click on the “Add to Cart” icon under any product (e.g., iPhone or MacBook). 4- Open the Shopping Cart page. 5.In the “Quantity” field for any product, enter alphabetic characters (e.g., “MMM”). 6. Click the update (🔄) button. | The system should validate input and display a message such as “Quantity must be a number.” | The product is removed from the cart without any validation message. | High | Major

## Checkout
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_CHECKOUT_1 | Only "Cash On Delivery" is available — other payment methods are missing | open | developer | Mohamed | Chrome v140 | CH_13 | 1.Add any product to the cart. 2.Proceed to the Checkout page. 3.Navigate to the Payment Method section. 4.Observe the available payment options. | User should be able to choose among multiple payment methods | Only Cash On Delivery is shown. | Highest | Major
BUG_CHECKOUT_2 | Order comment field allows more than 600 characters without showing validation error | open | developer | Mohamed | Chrome v140 | CH_16 | 1.Navigate to the checkout / order placement page. 2.Locate the Order Comment or Additional Notes field. 3.Enter text exceeding 600 characters,then Observe | The system should prevent entering more than 600 characters | No error message is displayed. | Medium | Major
BUG_CHECKOUT_3 | Confirmation email is not received cause of using localhost | open | developer | Mohamed | Chrome v141 | CH_19 | 1- Complete checkout 2- Check inbox | Confirmation email is received | local host version | Medium

## Admin Work
Defect # | Bug Description | Status | Assigned To | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_ADMIN_01 | Error message display (object object) | New | Developer | Randa | Chrome v141 | TC_Order_002 | 1. Scroll to the Order History section. 2. Select the Processing status from the "Order Status" dropdown. 3. Enter a comment in the "Comment" field. 4. Click the "Add History" button. | The page refreshes (or updates), the new history entry (including status and comment) appears in the Order History table, and the main Order Status field reflects the new status (Processing). | Error message display (object object) | High | Critical
BUG_ADMIN_02 | The table reloads and displays the message "No results!". | New | Developer | Randa | Chrome v141 | TC_Order_005 | 1. Enter the partial customer name (kathy) into the 'Customer' filter field. 2. Click the 'Filter' button. | The table reloads, showing all orders placed by "Kathy Durr" (and any other customer containing the text 'kathy'). | The table reloads and displays the message "No results!". | High | Critical
BUG_ADMIN_03 | The table reloads and displays the message "No results!". | New | Developer | Randa | Chrome v141 | TC_Order_006 | 1. Select the status Processing from the 'Order Status' dropdown. 2. Click the 'Filter' button. | The table reloads, and every order in the list has the status Processing. | The table reloads and displays the message "No results!". | Highest | Critical
BUG_ADMIN_04 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v141 | TC_Order_008 | 1. Click the 'Add Order' button. 2. Do not fill out any required fields (First Name, Last Name, E-Mail, Telephone). 3. Click the 'Continue' button at the bottom. | Validation errors are displayed next to the missing required fields, and the user remains on Tab 1: Customer Details. | the system display message "Warning: You do not have permission to modify orders!" | Highest | Critical
BUG_ADMIN_05 | no action happend | New | Developer | Randa | Chrome v141 | TC_ADD_CUST_001 | 1. Fill out all required fields on the General tab. 2. Click the blue 'Save' button. | The user is redirected to the Customer List with a success message. The new customer is listed as a standard user. | no action happend | High | Critical
BUG_ADMIN_06 | no action happend | New | Developer | Randa | Chrome v141 | TC_ADD_CUST_002 | 1. Leave any required field on the General tab empty. 2. Click the 'Save' button. | Validation error messages are displayed next to the missing required fields, and the customer is NOT saved. | no action happend | Highest | Critical
BUG_ADMIN_07 | The table reloads and displays the message "No results!". | New | Developer | Randa | Chrome v141 | TC_CUST_003 | 1. Enter the e-mail into the 'E-Mail' filter field. 2. Click the 'Filter' button. | Only the customer matching that e-mail address is displayed. | The table reloads and displays the message "No results!". | High | Critical
BUG_ADMIN_08 | The table reloads and displays the message "No results!". | New | Developer | Randa | Chrome v141 | TC_CUST_005 | 1. Select 'Disabled' from the 'Status' dropdown. 2. Click the 'Filter' button. | Only customers with a 'Disabled' status are displayed. | The table reloads and displays the message "No results!". | High | Critical
BUG_ADMIN_09 | the system display message "Warning: You do not have permission to modify extension!" | New | Developer | Randa | Chrome v141 | TC_EXT_02 | 1. Navigate to the relevant category (Shipping). 2. Click the 'Install' button (green plus icon) next to the target extension. | A success message is displayed. The 'Install' button is replaced by the 'Uninstall' (red minus) and 'Edit' (blue pencil) buttons. | the system display message "Warning: You do not have permission to modify extension!" | High | Critical
BUG_ADMIN_10 | the system display message "Warning: You do not have permission to modify extension!" | New | Developer | Randa | Chrome v141 | TC_EXT_03 | 1. Navigate to the relevant category (Shipping). 2. Click the 'Uninstall' button (red minus icon) next to the target extension. | A success message is displayed. The 'Uninstall' and 'Edit' buttons are replaced by the 'Install' button. | the system display message "Warning: You do not have permission to modify extension!" | High | Critical
BUG_ADMIN_11 | the system display message "Warning: You do not have permission to modify extension!" | New | Developer | Randa | Chrome v141 | TC_EXT_05 | 1. Update various settings (e.g., change Status to Enabled, set a Cost). 2. Click the 'Save' button. 3. Re-edit to confirm changes persisted. | A success message is displayed, and the new configuration values are saved and reflected when the form is reloaded. | the system display message "Warning: You do not have permission to modify extension!" | High | Critical
BUG_ADMIN_12 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v141 | TC_LAY_02 | 1. Enter the Layout Name. 2. Click 'Save'. | The new layout is created, a success message is displayed, and the layout is visible in the list. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_13 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v141 | TC_BAN_01 | 1. Enter the Banner Name. 2. Navigate to the Banner Images tab. 3. Add one image row with a Title, Link, and Image. 4. Click 'Save'. | The new banner is created, a success message is displayed, and the banner is visible in the list. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_14 | when click save no action happend | New | Developer | Randa | Chrome v141 | TC_RET_03 | 1. Click 'Add New'. 2. Enter the Order ID (1010) and select the Customer and Product. 3. Manually fill in the quantity, reason, and action details. 4. Click 'Save'. | A new return entry is successfully created and linked to the specified Order ID and customer. | when click save no action happend | High | Critical
BUG_ADMIN_15 | when click save no action happend | New | Developer | Randa | Chrome v141 | TC_RET_04 | 1. View the return and navigate to the History tab. 2. Select the new In Progress status. 3. Check the Notify Customer box. 4. Enter a Comment. 5. Click Add History. | The return status is updated to In Progress. The change is logged in the history, and the system attempts to send a notification email. | when click save no action happend | High | Critical
BUG_ADMIN_16 | the system display message "Warning: You do not have permission to modify returns!" | New | Developer | Randa | Chrome v141 | TC_RET_05 | 1. Select the test return using the checkbox in the list view. 2. Click the 'Delete' button. 3. Confirm the action. | The selected return request is permanently removed from the list, and a success message is displayed. | the system display message "Warning: You do not have permission to modify returns!" | High | Critical
BUG_ADMIN_17 | the system display message "Warning: You do not have permission to modify vouchers!" | New | Developer | Randa | Chrome v141 | TC_VOU_02 | 1. Leave all recipient/sender fields and Amount empty. 2. Click the 'Save' button. | The system prevents saving, and error messages are displayed next to the required empty fields. | the system display message "Warning: You do not have permission to modify vouchers!" | High | Critical
BUG_ADMIN_18 | the system display message "Warning: You do not have permission to modify vouchers!" | New | Developer | Randa | Chrome v141 | TC_VOU_03 | 1. Fill in all mandatory fields with valid data. 2. Select a Theme. 3. Click 'Save'. | The new voucher is created, a success message is displayed, and the entry is visible in the list with the correct Amount and Status. | the system display message "Warning: You do not have permission to modify vouchers!" | High | Critical
BUG_ADMIN_19 | the system display message "Warning: You do not have permission to modify vouchers!" | New | Developer | Randa | Chrome v141 | TC_VOU_04 | 1. Edit the existing voucher. 2. Change the Status to Disabled. 3. Click 'Save'. 4. Verify the change in the list view. | The voucher status is successfully updated to Disabled, rendering the code unusable. | the system display message "Warning: You do not have permission to modify vouchers!" | High | Critical
BUG_ADMIN_20 | the system display message "Warning: You do not have permission to modify voucher themes!" | New | Developer | Randa | Chrome v141 | TC_VOU_05 | 1. Select the test voucher using the checkbox in the list view. 2. Click the 'Delete' button. 3. Confirm the deletion. | The selected voucher is permanently removed from the list, and a success message is displayed. | the system display message "Warning: You do not have permission to modify voucher themes!" | High | Critical
BUG_ADMIN_21 | the system display message "Warning: This voucher cannot be deleted as it is part of an order!" | New | Developer | Randa | Chrome v141 | TC_THM_01 | 1. Enter the Theme Name. 2. Upload a valid Image. 3. Click 'Save'. | The new theme is created, a success message is displayed, and the theme is visible in the list. | the system display message "Warning: This voucher cannot be deleted as it is part of an order!" | High | Critical
BUG_ADMIN_22 | the system display message "Warning: You do not have permission to modify campaign" | New | Developer | Randa | Chrome v141 | TC_MKT_02 | 1. Fill in all mandatory fields with valid data. 2. Click 'Save'. | The new campaign is created, a success message is displayed, and the entry is visible in the list with Clicks initialized to 0. | the system display message "Warning: You do not have permission to modify campaign" | High | Critical
BUG_ADMIN_23 | the system display message "Warning: You do not have permission to modify coupons!" | New | Developer | Randa | Chrome v141 | TC_COU_01 | 1. Fill in mandatory fields. 2. Set Type to Fixed Amount and Discount to 10.00. 3. Set a future Date Start and Date End. 4. Click 'Save'. | The coupon is created, and the list reflects the Fixed Amount Type and the correct discount value. | the system display message "Warning: You do not have permission to modify coupons!" | High | Critical
BUG_ADMIN_24 | the system display message "Warning: You do not have permission to send emails" | New | Developer | Randa | Chrome v141 | TC_MAIL_02 | 1. Select Customer Group: VIP in the To field. 2. Enter a valid Subject and Message. 3. Click the 'Send' button. | The system confirms the message is queued for sending (or sends immediately) and a success confirmation message is displayed, confirming targeting the VIP group. | the system display message "Warning: You do not have permission to send emails" | High | Critical
BUG_ADMIN_25 | the system display message "Warning: You do not have permission to modify a store location" | New | Developer | Randa | Chrome v141 | TC_MAIL_03 | 1. Select All Customers in the To field. 2. Enter content. 3. Click 'Send'. | The system successfully queues/sends the message, and a success confirmation is displayed. | the system display message "Warning: You do not have permission to modify a store location" | High | Critical
BUG_ADMIN_26 | the system display message "Warning: You do not have permission to send emails" | New | Developer | Randa | Chrome v141 | TC_SLOC_01 | 1. Fill in Name, Address, and Telephone. 2. Set Status to Enabled. 3. Click 'Save'. | The new store location is created, a success message is displayed, and the entry is visible in the list. | the system display message "Warning: You do not have permission to send emails" | High | Critical
BUG_ADMIN_27 | the system display message "Warning: You do not have permission modify language" | New | Developer | Randa | Chrome v141 | TC_LANGL_02 | 1. Enter all required and optional fields with valid test data for Spanish. 2. Click 'Save'. | The new language is created, a success message is displayed, and the entry is visible in the list with the correct details. | the system display message "Warning: You do not have permission modify language" | High | Critical
BUG_ADMIN_28 | the system display message "Warning: You do not have permission modify currencies" | New | Developer | Randa | Chrome v141 | TC_CURR_02 | 1. Enter all required fields for Euro. 2. Set Status to Enabled. 3. Click 'Save'. | The new currency is created, a success message is displayed, and the entry is visible in the list with the correct symbol and rate. | the system display message "Warning: You do not have permission modify currencies" | High | Critical
BUG_ADMIN_29 | the system display message "Warning: You do not have permission modify currencies" | New | Developer | Randa | Chrome v141 | TC_CURR_03 | 1. Note the current Value and Date Updated for all non-default currencies. 2. Click the Update button on the Currency list page. | The Value and Date Updated fields for all non-default currencies are refreshed and show new, current rates. A success message for the update is displayed. | the system display message "Warning: You do not have permission modify currencies" | High | Critical
BUG_ADMIN_30 | the system display message "Warning: You do not have permission modify stock" | New | Developer | Randa | Chrome v141 | TC_SSTAT_01 | 1. Enter a new, unique Stock Status Name (e.g., "Limited Stock"). 2. Click 'Save'. | The new stock status is created, a success message is displayed, and the entry is visible in the list. | the system display message "Warning: You do not have permission modify stock" | High | Critical
BUG_ADMIN_31 | the system display message "Warning: You do not have permission modify stock" | New | Developer | Randa | Chrome v141 | TC_SSTAT_02 | 1. Select the test status linked to Product X. 2. Click the 'Delete' button. 3. Confirm the action. | The system displays a warning or error message, preventing deletion due to existing product dependencies. | the system display message "Warning: You do not have permission modify stock" | High | Critical
BUG_ADMIN_32 | the system display message "Warning: You do not have permission modify order status" | New | Developer | Randa | Chrome v141 | TC_OSTAT_02 | 1. Enter a new, unique Order Status Name (e.g., "Ready for Pickup"). 2. Click 'Save'. | The new order status is created, a success message is displayed, and the entry is visible in the list. | the system display message "Warning: You do not have permission modify order status" | High | Critical
BUG_ADMIN_33 | the system display message "Warning: You do not have permission modify order status" | New | Developer | Randa | Chrome v141 | TC_OSTAT_03 | 1. Attempt to select the Pending status and click the 'Delete' button. | The system prevents deletion and displays an error message stating, "Cannot delete a status that is currently assigned as a system default order status." | the system display message "Warning: You do not have permission modify order status" | High | Critical
BUG_ADMIN_34 | the system display message "Warning: You do not have permission modify countries" | New | Developer | Randa | Chrome v141 | TC_CNTY_02 | 1. Select the Atlantis country using the checkbox. 2. Click the 'Delete' button. 3. Confirm the action. | The selected country is permanently removed from the list, and a success message is displayed. | the system display message "Warning: You do not have permission modify countries" | High | Critical
BUG_ADMIN_35 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v142 | TC_Order_09 | 1. Enter valid data into all required fields. 2. Click the 'Continue' button. | The user successfully navigates to Tab 2: Products. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_36 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v143 | TC_Order_10 | 1. Type a valid product name (e.g., MacBook) into the product search bar. 2. Select the product from the autocomplete list. 3. Click the 'Add Product' button. | The selected product (MacBook) is added to the order list within the tab, showing quantity and price. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_37 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v144 | TC_Order_11 | 1. Type the invalid product name into the search bar. 2. Check the autocomplete dropdown. | The autocomplete dropdown either shows a "No results" message or remains empty. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_38 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v145 | TC_Order_12 | 1. Click the 'Continue' button (or directly click Tab 3: Payment Details). | The user successfully navigates to Tab 3: Payment Details. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_39 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v146 | TC_Order_13 | 1. Fill out all required fields in Tabs 3 (Payment) and 4 (Shipping). 2. Navigate to Tab 5: Totals. 3. Click the 'Save' button. | The user is redirected back to the Orders List Page, and a success message confirming the order creation is displayed. The new order appears at the top of the list. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_40 | the system display message "Warning: You do not have permission to modify orders!" | New | Developer | Randa | Chrome v147 | TC_Order_14 | 1. Click the 'Cancel' button at the top right of the page. | The user is redirected back to the main Orders List Page without saving any order data. | the system display message "Warning: You do not have permission to modify orders!" | High | Critical
BUG_ADMIN_41 | system display "No result" | New | Developer | Randa | Chrome v148 | TC_ADVPR_01 | 1. Enter the Q2 date range. 2. Click 'Filter'. | The report only includes sales figures from Q2. Products that only sold in Q1 are excluded. | system display "No result" | Medium | Critical