## Report
No | Module Name | TC_ID | Test Suite Name | Number of TCs | Total No | Done By | No of Passed TCs | No of Failed TCs | No of Bugs | No of Bugs | No of TCs Blocked | Pass Rate % |  |  | Total No of TCs = 426
1 | Registration | REG | Register | 14 | 27 | Ghada | 14 | 0 |  |  |  | 100 | 92.5926 | 92.5926 |  | N | %
|  | LOGIN | Login | 5 |  |  | 5 | 0 |  |  |  | 100 |  |  | Passed TCs | 354 | 83.0986
|  | FP | Forgot Password | 6 |  |  | 4 | 2 | 2 | 2 | 0 | 66.6667 |  |  | Failed TCs | 72 | 16.9014
|  | LOGOUT | Logout | 2 |  |  | 2 | 0 |  |  |  | 100
2 | Account | AC_LO | Account_LoggedOut | 4 | 124 | Ghada | 4 | 0 |  |  |  | 100 | 94.4 | 94.3548
|  | DASH | Dashboard | 12 |  |  | 12 | 0 |  |  |  | 100
|  | SB | Sidebar | 12 |  |  | 12 | 0 |  |  |  | 100
|  | EAC | Edit_Account | 10 |  |  | 10 | 0 |  |  |  | 100
|  | CP | Change_Password | 6 |  |  | 6 | 0 |  |  |  | 100
|  | AB | Address_Book | 22 |  |  | 20 | 2 | 2 | 2 | 0 | 90.9091
|  | WL | Wishlist | 8 |  |  | 7 | 1 | 1 | 1 | 0 | 100
|  | ORD | Orders | 12 |  |  | 12 | 0 |  |  |  | 100
|  | DL | Downloads | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | SBS | Subscriptions | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | RP | Rewards Points | 4 |  |  | 4 | 0 |  |  |  | 100
|  | RET | Returns | 6 |  |  | 6 | 0 |  |  |  | 100
|  | TS | Transactions | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | NL | Newsletter | 5 |  |  | 4 | 1 | 1 | 1 | 0 | 80
|  | AAC | Affiliate Account | 10 |  |  | 10 | 0 |  |  |  | 100
|  | AH | Account Tab In Header | 4 |  |  | 4 | 0 |  |  |  | 100
3 | Product Page | PP | Product Page | 25 | 25 | Mohamed | 20 | 5 | 5 | 5 | 0 | 80 | 80 | 80
4 | Category Page | CP | Category Page | 29 | 29 | Mohamed | 27 | 2 | 2 | 2 | 0 | 94.1176 | 93.1 | 93.1034
5 | Compare Page | CMP | Compare Page | 12 | 12 | Mohamed | 11 | 1 | 1 | 1 | 0 | 93.3333 | 91.7 | 91.6667
6 | Cart Management | CART | Cart | 49 | 49 | Menna | 39 | 10 | 11 | 11 | 0 | 79.5918 | 79.5918 | 79.5918
7 | Checkout | Checkout | Checkout | 20 | 20 | Randa | 17 | 3 | 1 | 2 | 1 | 85 | 85 | 85
8 | Admin Work | TC_LOGIN | Login | 5 | 96 | Hesham | 5 | 0 |  |  |  | 100 | 57.2917 | 57.2917
|  | TC_LOGOUT | Logout | 2 |  |  | 2 | 0 |  |  |  | 100
|  | TC_DASH | Dashboard | 3 |  |  | 3 | 0 |  |  |  | 100
|  | TC_Order | Orders | 14 |  |  | 4 | 10 | 10 | 3 | 7 | 28.5714
|  | TC_ADD_CUST | Add Customer | 2 |  |  | 0 | 2 | 2 | 2 | 0 | 0
|  | TC_CUST | Customer Management | 9 |  |  | 7 | 2 | 2 | 2 | 0 | 77.7778
|  | TC_UTIL | User Interface | 3 |  |  | 3 | 0 |  |  |  | 100
|  | TC_EXT | Extensions List | 5 |  |  | 2 | 3 | 3 | 0 | 3 | 40
|  | TC_LAY | Layout List | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | TC_BAN | Banner List | 1 |  |  | 0 | 1 | 1 | 0 | 1 | 0
|  | TC_RET | Returns List | 5 |  |  | 2 | 3 | 3 | 2 | 1 | 40
|  | TC_VOU | Gift Voucher List | 5 |  |  | 1 | 4 | 4 | 1 | 3 | 20
|  | TC_THM | Voucher Themes List | 1 |  |  | 0 | 1 | 1 | 0 | 1 | 0
|  | TC_MKT | Marketing List | 2 |  |  | 1 | 1 | 1 | 0 | 1 | 50
|  | TC_COU | Coupon List | 1 |  |  | 0 | 1 | 1 | 0 | 1 | 0
|  | TC_MAIL | Mail Form | 3 |  |  | 1 | 2 | 2 | 0 | 2 | 33.3333
|  | TC_SLOC | Store Location List | 1 |  |  | 0 | 1 | 1 | 0 | 1 | 0
|  | TC_LANGL | Language List | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | TC_CURR | Currency List | 4 |  |  | 2 | 2 | 2 | 0 | 2 | 50
|  | TC_SSTAT | Stocks Status List | 2 |  |  | 0 | 2 | 2 | 0 | 2 | 0
|  | TC_OSTAT | Order Status List | 3 |  |  | 1 | 2 | 2 | 0 | 2 | 33.3333
|  | TC_CNTY | Countries List | 3 |  |  | 2 | 1 | 1 | 0 | 1 | 66.6667
|  | TC_ZONE | Zones List | 1 |  |  | 1 | 0 |  |  |  | 100
|  | TC_ADVSA | Advanced Sales | 6 |  |  | 6 | 0 |  |  |  | 100
|  | TC_ADVSP | Advanced Sales Profit | 4 |  |  | 4 | 0 |  |  |  | 100
|  | TC_ADVPR | Advanced Products | 2 |  |  | 1 | 1 | 1 | 1 | 0 | 50
|  | TC_ADVPP | Advanced Products Profits | 2 |  |  | 2 | 0 |  |  |  | 100
|  | TC_ADVCU | Advanced Customers | 1 |  |  | 1 | 0 |  |  |  | 100
9 | Database | DB_CUS | Customers | 5 | 20 | Mohamed | 5 | 0 |  |  |  | 0 | 95 | 95
|  | DB_ORD | Orders | 5 |  |  | 5 | 0 |  |  |  | 0
|  | DB_PROD | Products | 5 |  |  | 4 | 1 |  | 1 | 0 | 0
|  | DB_ADD | Addresses | 5 |  |  | 5 | 0 |  |  |  | 0
10 | API | API_USER | Users | 6 | 6 | Menna | 6 | 0 |  |  |  | 100 | 100
|  | API_POST | Posts | 6 | 6 | Randa | 6 | 0 |  |  |  | 100
|  | API_COM | Comments | 6 | 6 | Ghada | 6 | 0 |  |  |  | 100
|  | API_DO | Todo | 6 | 6 | Mohamed | 6 | 0 |  |  |  | 100

## Summary
No |  | TC_ID | Module Name | Number of TCs | Total No | Done By | No | Module Name | Number of TCs | Done By | No of Passed TCs | No of Failed TCs | Pass Rate %
1 | Register | REG | Registration | 24 | 27 | Ghada | 1 | Registration | 27 | Ghada | 25 | 2 | 92.5926
| Login | LOGIN | Registration | 10 |  |  | 2 | Account | 124 | Ghada | 117 | 7 | 94.3548
| Forgot Password | FP | Registration | 13 |  |  | 3 | Product Page | 25 | Mohamed | 20 | 5 | 80
| Logout | LOGOUT | Registration | 2 |  |  | 4 | Category Page | 29 | Mohamed | 27 | 2 | 93.1034
2 | Account_LoggedOut | AC_LO | Account | 4 | 124 | Ghada | 5 | Compare Page | 12 | Mohamed | 11 | 1 | 91.6667
| Dashboard | DASH | Account | 12 |  |  | 6 | Cart Management | 49 | Menna | 39 | 10 | 79.5918
| Sidebar | SB | Account | 12 |  |  | 7 | Checkout | 20 | Randa | 17 | 3 | 85
| Edit_Account | EAC | Account | 10 |  |  | 8 | Admin Work | 96 | Hesham | 55 | 41 | 57.2917
| Change_Password | CP | Account | 6 |  |  | 9 | Database | 20 | Mohamed | 19 | 1 | 95
| Address_Book | AB | Account | 22 |  |  | 10 | API Users | 6 | Menna | 6 | 0 | 100
| Wishlist | WL | Account | 8 |  |  | 11 | API Posts | 6 | Randa | 6 | 0 | 100
| Orders | ORD | Account | 12 |  |  | 12 | API Comments | 6 | Ghada | 6 | 0 | 100
| Downloads | DL | Account | 3 |  |  | 13 | API Todo | 6 | Mohamed | 6 | 0 | 100
| Subscriptions | SBS | Account | 3 |  |  |  | Total | 426 |  | 354 | 72 | 83.0986
| Rewards Points | RP | Account | 4
| Returns | RET | Account | 6
| Transactions | TS | Account | 3
| Newsletter | NL | Account | 5
| Affiliate Account | AAC | Account | 10
| Account Tab In Header | AH | Account | 4
3 | Product Page | PP | Product Page | 25 | 25 | Mohamed
4 | Category Page | CP | Category Page | 34 | 34 | Mohamed
5 | Compare Page | CMP | Compare Page | 15 | 15 | Mohamed
6 | Database | DB | Database | 20 | 20 | Mohamed
7 | Cart | CART | Cart Management | 49 | 49 | Menna
8 | Checkout | Checkout | Checkout | 20 | 20 | Randa
9 | Login | TC_LOGIN | Admin Work | 5 | 96 | Hesham
| Logout | TC_LOGOUT | Admin Work | 2
| Dashboard | TC_DASH | Admin Work | 3
| Orders | TC_Order | Admin Work | 14
| Add Customer | TC_ADD_CUST | Admin Work | 2
| Customer Management | TC_CUST | Admin Work | 9
| User Interface | TC_UTIL | Admin Work | 3
| Extensions List | TC_EXT | Admin Work | 5
| Layout List | TC_LAY | Admin Work | 3
| Banner List | TC_BAN | Admin Work | 1
| Returns List | TC_RET | Admin Work | 5
| Gift Voucher List | TC_VOU | Admin Work | 5
| Voucher Themes List | TC_THM | Admin Work | 1
| Marketing List | TC_MKT | Admin Work | 2
| Coupon List | TC_COU | Admin Work | 1
| Mail Form | TC_MAIL | Admin Work | 3
| Store Location List | TC_SLOC | Admin Work | 1
| Language List | TC_LANGL | Admin Work | 3
| Currency List | TC_CURR | Admin Work | 4
| Stocks Status List | TC_SSTAT | Admin Work | 2
| Order Status List | TC_OSTAT | Admin Work | 3
| Countries List | TC_CNTY | Admin Work | 3
| Zones List | TC_ZONE | Admin Work | 1
| Advanced Sales | TC_ADVSA | Admin Work | 6
| Advanced Sales Profit | TC_ADVSP | Admin Work | 4
| Advanced Products | TC_ADVPR | Admin Work | 2
| Advanced Products Profits | TC_ADVPP | Admin Work | 2
| Advanced Customers | TC_ADVCU | Admin Work | 1